## Sheet1
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Nagendra Babu Reddy | 10-02-2026 | PDF upload failed for files larger than allowed limit | Sprint 2 | Backend Module | Functional | Increased upload size and optimized file handling | 11-02-2026 | Closed | Working correctly after fix
2 | Nagendra Babu Reddy | 12-02-2026 | Incorrect text extraction for special characters in PDF | Sprint 2 | Text Processing Module | Data Processing | Improved preprocessing and encoding handling | 13-02-2026 | Closed | Extraction accuracy improved
3 | Nagendra Babu Reddy | 15-02-2026 | Chat response delay during first query | Sprint 3 | AI Retrieval Module | Performance | Optimized embedding retrieval pipeline | 16-02-2026 | Closed | Latency reduced
4 | Nagendra Babu Reddy | 18-02-2026 | UI not updating after document processing | Sprint 3 | Frontend Module | UI Bug | Fixed UI state refresh after processing | 19-02-2026 | Closed | UI refresh issue resolved